## Instructions
Cross-Site Process Transfer Checklist – Instructions
Purpose:
Use this checklist to evaluate and document readiness across all functional areas before transferring a process or tool to a new site.
How to Use:
- Each row reflects a critical activity or check required to support successful tech transfer.
- Mark 'Relevant?' as Yes or No depending on applicability to the specific process/tool being transferred.
- Assign a responsible team or person in the 'Completion Owner' column.
- Track task status using the Status column (Open / In Progress / Complete).
- Use the Notes column for local adaptations, clarifications, or follow-ups.
This file includes:
- A main checklist covering Equipment, Documentation, Process, Materials, MES, QA, and Training elements.
- A dropdown sheet for controlled inputs.
- A change log to track version history.

## Cross-Site Checklist
Category | Transfer Element | Relevant? | Completion Owner | Status | Notes
Equipment & Physical Setup
Equipment & Physical Setup | Tool spec verified for receiving site | Yes | J. Villanueva | In Progress
Equipment & Physical Setup | Power, gas, HVAC utility alignment confirmed | No
Equipment & Physical Setup | Facility layout supports tool footprint
Equipment & Physical Setup | Tool installation guide shared
Equipment & Physical Setup | IQ/OQ plan reviewed with receiving site
Process & Recipe
Process & Recipe | Recipe settings matched across sites
Process & Recipe | Site-specific override values reviewed
Process & Recipe | Control parameters locked and released
Process & Recipe | Integration with existing process flow confirmed
Process & Recipe | Stability across consumable life tested
Documentation
Documentation | SOPs transferred and site-formatted
Documentation | WI/BOM reviewed by receiving team
Documentation | Batch record template adapted
Documentation | Calibration protocols shared
Materials & Supply Chain
Materials & Supply Chain | Approved vendor list reviewed
Materials & Supply Chain | Local stocking levels confirmed
Materials & Supply Chain | Material spec compatibility verified
Materials & Supply Chain | Logistic constraints reviewed (e.g., cold chain)
Automation & MES
Automation & MES | MES routing replicated and tested
Automation & MES | Alarm limits ported and verified
Automation & MES | Data mapping reviewed for site SCADA
Automation & MES | Batch tracking enabled
Training & Communication
Training & Communication | Training plan delivered to receiving operators
Training & Communication | Troubleshooting guides updated and shared
Training & Communication | Daily standup ownership transitioned
Training & Communication | Engineering point of contact assigned
QA & Compliance
QA & Compliance | Site-specific change control approved
QA & Compliance | Deviation handling process aligned
QA & Compliance | Risk assessment reviewed with QA
QA & Compliance | Regulatory implications considered

## Dropdown Options
Category
Equipment & Physical Setup
Process & Recipe
Documentation
Materials & Supply Chain
Automation & MES
Training & Communication
QA & Compliance

## Change Log
Version | Change Description | Author | Date
v1 | Initial draft of cross-site process transfer checklist template | Josh Villanueva | 2025-06-29