## Instructions
Cross-Site Change Tracker – Instructions
Purpose:
This tracker is used to monitor changes made at a source (origin) site and their adoption status across destination sites.
It supports coordination and visibility during multi-site process or equipment transfers.
How to Use:
- Each row in the tracker represents a single change initiated at a source site.
- 'Change Type' uses dropdown options: Process / Equipment / Documentation / Material / Other.
- 'Adoption Status' tracks if the change has been rolled out to destination sites.
- Track who owns adoption execution separately from change initiation.
- Use the 'Notes' field to capture context, blockers, or verification requirements.
Fields Explained:
- Change ID: Unique identifier for the change
- Change Type: Category of change
- Affected System: System or process impacted
- Description: Summary of the change content
- Origin Site: Where the change was initiated
- Destination Site(s): Site(s) where adoption is required
- Change Owner: Person or team that initiated the change
- Date Initiated: When the change was logged
- Target Adoption Date: Intended date for full rollout
- Adoption Owner: Person/team driving adoption at receiving site(s)
- Adoption Status: Status of adoption (Not Started / In Progress / Completed / N/A)
- Notes: Freeform notes (e.g., deviations, follow-ups)

## Change Tracker
Change ID | Change Type | Affected System | Description | Origin Site | Destination Site(s) | Change Owner | Date Initiated | Target Adoption Date | Adoption Owner | Adoption Status | Notes
CH-001 | Process | Upstream Media Prep | Switch from XDM4 to XDM5 due to supply constraints | Site A | Site B, Site C | PD Team | 2025-06-01 | 2025-07-01 | MSAT B | In Progress | Pending filter validation at Site C
CH-002 | Material | Single-Use Tubing Set | Update tubing set SKU to new vendor-qualified part | Site B | Site A | Manufacturing | 2025-06-03 | 2025-07-10 | Eng A | Not Started | QA approval pending
CH-003 | Documentation | Batch Record | Add clarification to harvest step timing | Site A | Site D | QA | 2025-05-28 | 2025-06-30 | Doc Control | Completed | Training confirmed by destination
CH-004 | Equipment | Bioreactor Controller | Firmware patch from v1.2 to v1.3 to fix temp bug | Site C | Site A, Site B | Automation | 2025-06-10 | 2025-07-15 | Facilities | In Progress | Tech team awaiting patch release

## Dropdown Options
Change Type Options | Sample Site List
Process | Site A
Equipment | Site B
Documentation | Site C
Material | Site D
Other

## Change Log
Version | Change Description | Author | Date
v1 | Initial draft of cross-site change tracker with biotech-aligned examples | Josh Villanueva | 2025-06-27