## Instructions
Engineering Ownership Matrix – Instructions
Purpose:
This matrix defines the transition of engineering task ownership across process maturity levels.
It supports the dev-to-sustaining handoff for processes originally owned by a single team.
How to Use:
- Each row represents a granular engineering task. Modify tasks to suit your organization.
- Columns L1–L4 define ownership at each maturity level.
- Ownership can be Development, Sustaining, or Joint depending on process stage.
- Notes explain the rationale for ownership transitions.
Maturity Levels:
Level 1 – Safety + Process Definition
Level 2 – Key Infrastructure In Place
Level 3 – Process Control Structure Established
Level 4 – Stability Achieved Over Time

## Ownership Matrix
Task | Category | Level 1 | Level 2 | Level 3 | Level 4 | Notes
Safety review complete | Safety Infrastructure | Development | Development | Joint | Sustaining | Dev initiates hazard analysis and training; Sustaining ensures compliance over time
Reagent handling infrastructure validated | Safety Infrastructure | Development | Joint | Sustaining | Sustaining | Dev ensures initial validation; Sustaining takes ownership as production scales
Tool install and config | PM / Equipment Readiness | Development | Development | Joint | Sustaining | Dev owns setup, IQ/OQ; Sustaining manages ops and post-maintenance checks
DOEs for process recipe definition | Process / Equipment Definition | Development | Development | Joint | Sustaining | Dev defines recipe and parameters; Sustaining manages drift and lock control
Consumables specification and setup | Process / Equipment Definition | Development | Joint | Sustaining | Sustaining | Dev evaluates and qualifies; Sustaining handles usage tracking and updates
MES integration testing | Automation Infrastructure | Development | Development | Joint | Sustaining | Dev owns validation; Sustaining manages change control and reliability
FDC setup and alarm configuration | Automation Infrastructure | Development | Development | Joint | Sustaining | Dev defines metrics and thresholds; Sustaining reviews and maintains alarms
Rework SOP definition | SOP Completeness | Development | Joint | Sustaining | Sustaining | Dev defines early procedures; Sustaining refines based on ops experience
Production run SOP finalization | SOP Completeness | Development | Development | Joint | Sustaining | SOPs mature with the process; Sustaining trains and enforces usage
SPC chart setup and review | SPC Baseline & Control | Development | Joint | Sustaining | Sustaining | Dev builds charts; Sustaining monitors and responds after stabilization
Process metric baseline definition | SPC Baseline & Control | Development | Development | Joint | Sustaining | Dev derives baseline; Sustaining uses for control and alerts
Inline defect signal debug | Deviation Management | Development | Development | Joint | Sustaining | Dev investigates root cause; Sustaining applies known fixes and trends
CAPA execution and tracking | Deviation Management | Development | Joint | Sustaining | Sustaining | Dev may trigger CAPA; Sustaining ensures follow-through and effectiveness
Transfer package assembly | Transfer Package Readiness | Development | Development | Joint | Sustaining | Dev assembles docs and parameters; Sustaining reviews and uses
Training of receiving team | Transfer Package Readiness | Development | Joint | Joint | Sustaining | Dev supports early training; Sustaining formalizes and refreshes
NPI processing at operation | Transfer Package Readiness | Development | Joint | Joint | Sustaining | Dev owns pilot setup and early enablement; Sustaining ramps and owns after stabilization

## Change Log
Version | Change Description | Author | Date
v1 | Initial version of engineering task ownership matrix | J. Villanueva | 2025-06-26

## Dropdown Options
Category
Safety Infrastructure
PM / Equipment Readiness
Process / Equipment Definition
Automation Infrastructure
SOP Completeness
SPC Baseline & Control
Deviation Management
Transfer Package Readiness