## Instructions
FMEA and Continuous Improvement (CI) Project Tracker
This tracker is designed to support Failure Mode and Effects Analysis (FMEA) alongside continuous improvement (CI) ownership tracking.
Each failure mode is evaluated based on Severity, Occurrence, and Detection. The Risk Priority Number (RPN) is calculated as: RPN = Severity × Occurrence × Detection.
Use this to prioritize risk mitigation actions and track ownership, containment, and linked CI projects.
Scoring Guidelines (1–10 scale):
- Severity: 1 = negligible impact, 10 = catastrophic impact
- Occurrence: 1 = extremely rare, 10 = frequent or inevitable
- Detection: 1 = easily detected, 10 = undetectable prior to failure
Dropdowns are provided for Status and Containment fields.
CI Projects that address specific failure modes can be linked using the CI Project ID column.
This file contains:
- Main FMEA Log (with sample biotech-relevant entries)
- Continuous Improvement (CI) Project Tracker
- Change Log for version tracking

## FMEA Log
Process Step | Failure Mode | Effect | Severity | Occurrence | Detection | RPN | Owner | Status | Containment Implemented? | CI Project ID | Notes
Cell Expansion | Bioreactor temp excursion | Cell viability loss | 9 | 3 | 4 | 108 | Process Eng | In Progress | Yes | CI-001 | Monitor spike noted in last 3 runs
Harvest | Filter clogging | Yield reduction | 7 | 4 | 3 | 84 | Manufacturing | Open | No | CI-002 | More frequent prefilter replacement under eval
Formulation | Incorrect buffer addition | Incorrect pH | 8 | 2 | 5 | 80 | QA | Closed | Yes | CI-003 | Operator retraining completed
Cryopreservation | Cryobag leak | Loss of product | 10 | 2 | 6 | 120 | Facilities | Open | No |  | Vendor lot variation suspected
Final Labeling | Wrong label version | Regulatory noncompliance | 9 | 2 | 7 | 126 | QA | Closed | Yes | CI-004 | Barcode scanner implemented

## CI Project Tracker
CI Project ID | Linked Failure Mode(s) | Owner | Target Date | Status | Notes/Outcome Summary
CI-001 | Bioreactor temp excursion | Process Eng | 2025-07-15 | In Progress | Evaluating new sensor calibration schedule
CI-002 | Filter clogging | Manufacturing | 2025-07-10 | Planned | Trial of dual prefilter configuration

## Dropdown Options
Owner
Process Eng
Manufacturing
QA
Facilities

## Change Log
Version | Change Description | Author | Date
v1 | FMEA and CI Tracker created | Josh Villanueva | 2025-06-27