## Instructions
Scale-Up Risk Score Tracker – Instructions
Purpose:
This tracker helps quantify and visualize operational risk across scale-up readiness dimensions.
It is designed to support prioritization of mitigation efforts before formal tech transfer or process ramp.
How to Use:
- Each row captures a distinct risk area (e.g., documentation, supply chain, method robustness).
- Assign a risk domain, qualitative description, and numeric risk rating (1–5 scale).
- Use the 'Weight' column if certain categories should be weighted more heavily.
- The 'Weighted Score' column is automatically calculated: Risk Rating × Weight.
- The 'Reviewed?' column tracks whether the risk item has been formally assessed or mitigated.
- The Notes field should capture mitigation context or review rationale.
Risk Rating Reference (1–5 scale):
- 1 = Low / well-controlled
- 3 = Moderate / needs further alignment
- 5 = High / unclear ownership or high likelihood-impact
This file includes:
- Risk Score Log with sample biotech-relevant categories
- Dropdown Options tab for consistent review status and domains
- Change Log for version tracking

## Risk Score Log
Area / Category | Description | Risk Domain | Risk Rating (1–5) | Weight (Optional) | Weighted Score | Owner | Mitigation Notes | Reviewed?
Supply Chain Readiness | Primary reagent supplier has single-source risk | Materials | 4 | 1.5 | 6 | Supply Chain | Dual source qualification in progress | In Progress
Method Robustness | Process performance varies with operator | Process | 3 | 1 | 3 | PD Team | Retraining plan in place | Yes
Documentation Maturity | Batch records not yet finalized | Documentation | 5 | 1.2 | 6 | QA | Draft in review, SOP alignment pending | No
Facility Fit | Buffer room near capacity limits | Facilities | 2 | 1 | 2 | Facilities Eng | Expansion plan approved for next quarter | Yes
Training Completion | New operators untrained on latest step | Personnel | 3 | 1 | 3 | Manufacturing | Training scheduled next week | In Progress

## Dropdown Options
Area / Category | Risk Domains
Supply Chain Readiness | Materials
Method Robustness | Process
Documentation Maturity | Documentation
Facility Fit | Facilities
Training Completion | Personnel
Equipment
QA

## Change Log
Version | Change Description | Author | Date
v1 | Initial draft of scale-up risk score tracker with weighted scoring logic | Josh Villanueva | 2025-06-28