## Instructions
System Issue Investigation Tracker – Instructions
Purpose:
This tool supports structured, model-based troubleshooting of complex, cross-functional manufacturing or systems integration issues.
It is designed to track hypotheses, supporting/contradictory data, and ongoing experiment planning until root cause is identified and resolved.
Sheet Structure:
- 'Brainstorming': Guided template to help generate failure mode models across categories (Equipment, Process, Materials, Human, Environment).
- 'Model Tracker': Working log of each hypothesized model, evidence gathered, experiments planned, and disposition status.
- 'Change Log': Tracks edits and version updates.
How to Use:
1. Start by filling out the Brainstorming sheet to generate potential failure models.
2. For each viable model, log it as a row in the Model Tracker sheet.
3. Use newline-separated entries in cells for multiple evidence or planned experiments.
4. As experiments complete, move results into Evidence columns and update experiment status.
5. Track disposition for each model (Confirmed Root Cause, Not Root Cause, Contributor).
This asset supports high-quality problem solving and traceable investigation history across engineering, QA, and integration teams.

## Brainstorming
Problem Statement: | Low Cell Viability for Batch A and B
Owner: | Josh Villanueva
Date: | 2025-07-11
Data: | [link to data related to problem]
Category | Possible Failure Modes / Contributing Factors
Equipment | Bioreactor DO sensor miscalibration leads to incorrect DO conc
Equipment | Bioreactor DO sensor drift over time leads to changing DO conc
Equipment
Process | Buffer prep pH is consistently off by 0.2 units when mixed in large volume tanks
Process
Process
Materials | Raw media component from Lot #ABC is showing abnormal osmolality
Materials
Materials
People | Operator loaded cartridge in reverse orientation due to unclear SOP layout on GUI screen
People
People
Environment | Cold storage room compressor maintenance overdue, causing temperature excursions
Environment
Environment
Measurement / Data
Measurement / Data
Measurement / Data
Upstream / Incoming | Software bug in fill control loop causes premature cycle trigger
Upstream / Incoming
Upstream / Incoming

## Model Tracker
Model ID | Hypothesized Failure Mode / Model | Model Owner | Supporting Evidence (new line per entry) | Contradictory Evidence (new line per entry) | Next Steps (new line per entry with status/date/owner) | Current Disposition | Notes
M-001 | Bioreactor DO sensor miscalibration leads to incorrect DO conc | Process Eng 1 | - Batch A, B showed low viability and low DO - Historical sensor calibration issues | - Batch C with same operator and cell line passed with same sensor | - Recalibrate sensor and re-run DO stability check - Compare against off-line DO probe - Owner: QA Tech, Due: 7/18 | Open | Prioritized due to evidence pattern and ease of sensor validation [link data here]
M-002 | Bioreactor DO sensor drift over time leads to changing DO conc | Process Eng 1 | - Batch A, B showed low viability and low DO - DO trend over process drifts low to 90% setpoint - Historical sensor drift noted | - Batch C with same operator and cell line passed with same sensor | - Recalibrate sensor and re-run DO stability check - Compare against off-line DO probe - Owner: QA Tech, Due: 7/18 | Open | Prioritized due to evidence pattern and ease of sensor validation [link data here]
M-003 | Raw media component from Lot #ABC is showing abnormal osmolality | QA Chem | - Supplier CoA shows osmolality borderline - Similar low osmolality for lots #BCD (low viability Batch B) | - Batch C run with Lot #CDF showed normal viability with same bioreactor - Lot #CDF has similar osmolality to lot #BCD | - Send sample for third-party assay - Replace with known-good lot #XYZ and retest - Owner: QC Chemist, Due: 7/20 | Open | High priority due to impact across batches and low test burden [link data here]
M-004 | Operator loaded cartridge in reverse orientation due to unclear SOP layout on GUI screen | Training Lead | - Newer operators trained under Rev C SOP had 2x error rate - Line audit caught misoriented load |  | - Review Rev B vs Rev C SOP deltas - GUI mockup revision and training spot check planned - Owner: Ops Trainer, Due: 7/19 | Contributor | Moderate priority; action in parallel with process checks
M-005 | Buffer prep pH is consistently off by 0.2 units when mixed in large volume tanks | Process Eng 2 | - Large tank batches show pH setpoint offset and batch-to-batch pH variability - Small-scale benchtop batches show stable pH and viability - Historical data correlated lower viability with pH deviation | - inconsistent correlation between large tank batch vaibility and pH | - Repeat mixing in large tank with new SOP, verify pH hits setpoint, compare viability to small batch viability (use same cell line) - Owner: Process Dev, Due: 7/22 | Open | Med-High priority; mid-effort testing [link data here]
M-006 | Cold storage room compressor maintenance overdue, causing temperature excursions | Facilities | - Temp logs show spikes every 48 hrs - Inventory loss recorded in same time frame | - Other freezers beyond maintenance due date show no temp instability | - Compressor inspection + log correlation underway - Owner: Facilities Tech, Due: 7/17 | Contributor | In Progress; low-cost confirmation
M-007 | Software bug in fill control loop causes premature cycle trigger | Automation | - Logs show fill stop trigger before weight threshold - Issue isolated to v2.3.1 firmware - Rollback to v2.3.0 resolves issue in test runs |  | - Monitor next batch viability after FW rollback - Perform regression test to confirm fill vs viability correlation - Owner: Automation Eng, Due: 7/19 | Leading Root Cause Model | Resolved fill issue, validation In Progress; check viability for Batch D and verify fill

## Change Log
Version | Change Description | Author | Date
v1 | Initial draft with instructions, brainstorming, and model tracker structure | Josh Villanueva | 2025-07-11