## Project Overview
PROJECT OVERVIEW – GANTT TRACKER
Initiative Name | Scale-Up Readiness for Process ABC
Initiative Owner / Champion | Josh Villanueva
Start Date | 2025-07-07
Target End Date | 2025-08-28
Overall Timeline Duration (Days) | 52
Context Notes | Tracks key readiness activities for process transfer, operational alignment, and tech transfer milestones.

## Instructions
Scale-Up Readiness Gantt Tracker – Instructions
Purpose:
Use this file to plan and monitor readiness milestones during process scale-up or tech transfer preparation.
How to Use:
- Fill out tasks in the 'Project Tasks' sheet. Each row should be a specific deliverable tied to a function or readiness category.
- Phases are optional but help organize rollout stages (e.g., Phase 1 = pre-transfer, Phase 2 = readiness testing).
- Populate Start/End Dates to auto-calculate duration.
- Use 'Status' column to indicate whether the item is Open, In Progress, or Completed.
- The Gantt Chart auto-generates based on the Start/End Dates from the task list.
Other Sheets:
- 'Review Deadlines' captures important checkpoint dates for cross-functional reviews.
- 'Dropdown Options' includes editable list values for Status, Functions, and Phases.
- 'Change Log' captures tracker-level modifications or updates.

## Project Tasks
Area | Task | Owner | Function | Phase | Start Date | End Date | Duration (Days) | Status | Notes
Upstream | Finalize media prep SOP | Jenny T. | Process Dev | Phase 1 | 2025-07-01 | 2025-07-05 | 4 | In Progress | Review with QA pending
Facilities | Complete buffer room qualification | David N. | Facilities | Phase 1 | 2025-07-04 | 2025-07-11 | 7 | Not Started
Manufacturing | Train operators on cryo step | Linda P. | Manufacturing | Phase 2 | 2025-07-10 | 2025-07-14 | 4 | Not Started
QA | Verify batch record readiness | Raj S. | QA | Phase 2 | 2025-07-12 | 2025-07-16 | 4 | Not Started
Automation | Deploy updated control recipe | Emily K. | Automation | Phase 3 | 2025-07-15 | 2025-07-25 | 10 | Not Started
Supply Chain | Qualify 2nd cryobag vendor | Tina Y. | Supply Chain | Phase 3 | 2025-07-20 | 2025-07-30 | 10 | Not Started

## Review Deadlines
Milestone | Owner | Target Date | Status
SOP Completion Review | QA | 2025-07-08 | Planned
Operator Training Signoff | Manufacturing | 2025-07-14 | Planned
Process Control Validation | Automation | 2025-07-22 | Planned
Cryobag Vendor Approval | Supply Chain | 2025-07-30 | Planned

## Dropdown Options
QMS Areas | Area | Functions
Document Control | Upstream | Process Dev
Training & Qualification | Facilities | Facilities
Deviation Management | Manufacturing | Manufacturing
Audit Program | QA | QA
Change Management | Automation | Automation
Risk Management | Supply Chain | Supply Chain

## Change Log
Version | Change Description | Author | Date
v1 | Create Gantt Chart Tracker | Josh Villanueva | 2025-06-28