## Instructions
Process Readiness Tracker – Instructions (Updated 2025-06-26)
Purpose
This tracker helps cross-functional teams assess whether a process is operationally ready for handoff from development to sustaining, or from site-to-site transfer.
It captures readiness across safety, documentation, automation, process stability, compliance, and ownership infrastructure.
How to Use This Tracker
- Each row is a granular readiness task required for a process to be considered mature and transferable.
- Tasks are grouped by category bucket, which align directly with the maturity scorecard used for high-level transfer decisions.
- Each row includes a “Gating” field:
- Yes = must be completed for the category to be considered satisfied.
- No = optional or supporting readiness task.
Scoring Linkage
- This tracker feeds into the Process Maturity Scorecard.
- A category in the scorecard can be marked complete once all Gating = Yes tasks for that category are marked complete or verified.
- This model supports modular ownership transfer by establishing a minimum operational foundation for each readiness category.
Column Definitions
Scorecard Category | The maturity system category this task supports (e.g., Safety, SOP, Automation)
Requirement | A clearly defined task or capability to establish before handoff
Risk Level | Optional priority or impact label (Low / Medium / High)
Gating | Yes = required for scoring completion; No = optional or context-specific
Owner | Team or individual responsible for completing this task
Target Closure Date | Planned due date for task completion
Verified | Use to track QA sign-off, data validation, or other formal confirmation
Notes | Any relevant context, dependencies, or documentation links
Best Practices
- Use this tracker collaboratively across MSAT, PD, QA, and systems integration functions.
- Tailor tasks and gating status to what’s truly needed in your environment.
- This tool is most effective when paired with:
- A structured ownership matrix
- A defined handoff reviewer or forum
- Clear entry/exit criteria for transfer governance

## Process Readiness Tracker
Scorecard Category | Requirement | Risk Level | Gating | Owner | Target Closure Date | Verified | Notes
Safety Infrastructure
Safety Infrastructure | Safety review complete (Equipment and Process Hazards) | High | Yes | J. Kim | 2025-06-20 | No
Safety Infrastructure | Technician/Engineering Safety Training completed | High | Yes | A. Shah | 2025-06-20 | Yes
Safety Infrastructure | Reagent handling/mix/storage infrastructure in place and validated |  | Yes
Safety Infrastructure | Chemical handling SOP reviewed by EHS |  | Yes
Safety Infrastructure | Emergency shutdown procedure posted and trained |  | Yes
Safety Infrastructure
Safety Infrastructure
Safety Infrastructure
Process / Equipment Definition
Process / Equipment Definition | Scope of process understood and documented (at operation + integrated process flow dependencies) |  | Yes
Process / Equipment Definition | Tool install and setup complete |  | Yes
Process / Equipment Definition | Facilties setup complete (gas and chemical hookups, electrical hookup) |  | Yes
Process / Equipment Definition | IT setup complete (connectivity to factory network/MES) |  | Yes
Process / Equipment Definition | Install Qual/Operational Qual complete (IQ/OQ) |  | Yes
Process / Equipment Definition | Equipment Consumables defined |  | Yes
Process / Equipment Definition | Equipment Settings defined |  | Yes
Process / Equipment Definition | Process Recipe (on Equipment) defined |  | Yes
Process / Equipment Definition | Operational Run (for Product and Quals) defined |  | Yes
Process / Equipment Definition | Process Qual complete (PQ) |  | Yes
Process / Equipment Definition | Standard Equipment Preventative Maintenance (PM) procedures defined |  | Yes
Process / Equipment Definition | PM schedule/frequency defined |  | Yes
Process / Equipment Definition | Tool Qual (post-PM/post-repair equipment health assessment) defined + Supporting Infrastructure |  | Yes
Process / Equipment Definition | Fault Detection Classififcation (FDC) enabled and alarm limits set |  | Yes
Process / Equipment Definition | Consumable management system within factory in place |  | Yes
Process / Equipment Definition | Key process metrics are understood and defined |  | Yes
Process / Equipment Definition
Process / Equipment Definition
Process / Equipment Definition
SOP Completeness
SOP Completeness | Consumables + Equipment Settings + Equipment Physical Config + Process Recipes Documented |  | Yes
SOP Completeness | Standard Production Run SOP |  | Yes
SOP Completeness | Rework SOP (tool abort, misprocess) |  | Yes
SOP Completeness | PM procedure SOP |  | Yes
SOP Completeness | Tool Qual SOP |  | Yes
SOP Completeness | Systematic Plan for handling non-standard material on standard operational setup documented |  | Yes
SOP Completeness | Systematic Plan for handling standard material on non-standard operational setup documented |  | Yes
SOP Completeness | Training matrix established for all process SOPs |  | Yes
SOP Completeness | Key process metrics are documented |  | Yes
SOP Completeness
SOP Completeness
SOP Completeness
Automation Infrastructure
Automation Infrastructure | Equipment and Operational Integration with Manufacturing Execution System (MES) tested and validated |  | Yes
Automation Infrastructure | Key process metrics from tool data are setup for automatic reporting and review |  | Yes
Automation Infrastructure | SPC charts setup with run data populating |  | Yes
Automation Infrastructure | SPC OOC's (out-of-control points) linked to notification system |  | Yes
Automation Infrastructure | FDC control charts setup with run data populating |  | Yes
Automation Infrastructure | FDC and Tool alarms linked to notification system |  | Yes
Automation Infrastructure | Automatic Response to OOC's or alarms setup and tested |  | Yes
Automation Infrastructure
Automation Infrastructure
Automation Infrastructure
Deviation Management
Deviation Management | SPC control and spec limits established from reasonable baseline |  | Yes
Deviation Management | FDC chart limits established based on equipment limitations and reasonable baseline |  | Yes
Deviation Management | Standarized responses to SPC and FDC OOC's established and documented |  | Yes
Deviation Management | Periodic review/reassessment of limits with standardized methodlogy established |  | Yes
Deviation Management | Deviation tracking system setup and active |  | Yes
Deviation Management | CAPA plan documented for all major deviations |  | Yes
Deviation Management | CAPA effectiveness reviews conducted periodically |  | Yes
Deviation Management | Deviation trends shared in readiness reviews |  | Yes
Deviation Management
Deviation Management
Deviation Management
QA & Compliance Infrastructure
QA & Compliance Infrastructure | Raw material qualification complete |  | Yes
QA & Compliance Infrastructure | Batch record template reviewed by QA |  | Yes
QA & Compliance Infrastructure | Batch record tracking and documentation system setup |  | Yes
QA & Compliance Infrastructure | Supply chain dependencies updated and confirmed |  | Yes
QA & Compliance Infrastructure | Deviations categorized + mitigation plans in place |  | Yes
QA & Compliance Infrastructure | Deviation SOP approved and live in QMS |  | Yes
QA & Compliance Infrastructure | Process changes logged and tracked with implementation date |  | Yes
QA & Compliance Infrastructure | Audit trail system enabled |  | Yes
QA & Compliance Infrastructure | Stability test method validated |  | Yes
QA & Compliance Infrastructure | QA-reviewed FMEA exists |  | Yes
QA & Compliance Infrastructure
QA & Compliance Infrastructure
QA & Compliance Infrastructure
Transfer Package Readiness
Transfer Package Readiness | Final parameter set documented |  | Yes
Transfer Package Readiness | Process parameter windows + process control limits documented |  | Yes
Transfer Package Readiness | Process training materials delivered and acknowledged (unit operation details + integrated flow interactions) |  | Yes
Transfer Package Readiness | Transfer package compiled into Transfer Package (configs/settings/recipes/SOPs/consumables/automation) |  | Yes
Transfer Package Readiness | Receiving team trained on startup/qualification requirements |  | Yes
Transfer Package Readiness | Cross-site variation/difference mapping documented (differencs in facilities, factory infrastructure, MES, environment, etc) |  | No
Transfer Package Readiness | Capacity modeling for volume scale up completed |  | No
Transfer Package Readiness | BOM and Process cost per unit caluclation completed |  | No
Transfer Package Readiness | Receiving team sign-off complete |  | Yes
Transfer Package Readiness
Transfer Package Readiness
Transfer Package Readiness

## Change Log
Version | Change Description | Author | Date
v1 | Initial tracker with section headers and pre-filled examples | J. Villanueva | 2025-06-24

## Dropdown Options
Scorecard Category
Safety Infrastructure
Process / Equipment Definition
SOP Completeness
Automation Infrastructure
Deviation Management
QA & Compliance Infrastructure
Transfer Package Readiness